## Stakeholder Analysis
Stakeholder Analysis
Stakeholder | Project Role | Category | Requirements | Communication Methods | Stakeholder Analysis Group
Project Sponsor Group | Sign off on major project decisions | Internal | ensure program alignment with groups vision, receive periodic updates, funding for program | meetings, presentations, reports | High Power/High Interest
Project Manager | Managing all aspects of the project | Internal | stakeholder collaboration, effective resource allocation, clear scope and objectives | regular team meetings and detailed reports | Medium Power/High Interest
Training Vendor | assist in curriculum development, delivering the training content, providing guidance, and facilitating hands-on sessions | External | clearly defined roles, supportive environment | meetings, feedback reports | Medium Power/High Interest
Technology provider | Providing hardware, software and technical assistance for the program | External | appropriate technology provision, regular support and maintenance | Phone calls, meetings | Medium Power/Medium Interest
Weavers | Beneficiaries of program | External | accessible training sessions, relevant curriculum | community meetings, announcements, awareness sessions | Low Power/High Interest
Local Community leaders | Support and promote the program | External | participation in decision making, alignment with community needs | community meetings, announcements, awareness sessions | Medium Power/High Interest
Educational Institution | Providing a facility for the program | External | Providing a facility for the program | memorandum of understanding, email, phone calls | Medium Power/Low Interest
Government Agency | Supporting skill development program | External | regulatory compliance, resource support | meetings, reports | High Power/Medium Interest
Media | Promoting awareness creation | External | accurate reporting | media interviews | Low Power/High Interest

## Risk Identification
Project | Training project
last updated
|  |  | Rank from 1 lowest to 5 highest | Rank from 1 lowest to 5 highest
Risk ID | Description | Trigger | Probability | Impact | Score | Owner | Response | Response Strategy | Expected Results | Status | Notes
1 | Limited internet access |  | 3 | 3 | 9 | Project Manager | Mitigate risk | Assess internet access through a survey, Provide offline resources where possible
2 | Resistance to Digital change |  | 2 | 5 | 10 | Project Sponsor | Mitigate risk | Implement a comprehensive change management strategy, including awareness campaigns and workshops
3 | Budget overruns |  | 2 | 4 | 8 | Finance Manager | Mitigate risk | Detailed Budget Development with contingency funds and management reserves, Regular monitoring
4 | Limited participation |  | 2 | 5 | 10 | Project Manager | Mitigate risk | Offer incentives to promote engagement, engage in targeted/door to door outreach
5 | Shortage of skilled instructors |  | 2 | 5 | 10 | Procurement Manager | Avoid risk | Secure funding early, explore technological partnerships
6 | Digital equipment acquisition issues |  | 1 | 4 | 4 | Procurement Manager | Accept | _ |  |  | Note: There is no response strategy as this risk's score is less than 9.
7 | Economic Downturn |  | 2 | 5 | 10 | Project Sponsor | Mitigate risk | Diversify funding sources, establish partnerships, and offer flexible participation options for economically impacted individuals.
8
9
10
11
12

## Communication Plan
DELIVERABLE INFORMATION | RECIPEIENT | PURPOSE | DELIVERY MEDIUM | FREQUENCY | OWNER | DELIVERABLE DOCUMENT
Initiation Meeting | All Stakeholders | To gather initial information for the initiation plan | Meeting (Face to face) | First Meeting before the project start date | Project Manager | Agenda
Meeting Minutes
Distribute Project Initiation Plan | All Stakeholders | Distribute plan to alert stakeholders of the project scope and to gain their buy in. | Emails | Before Kickoff meeting | Project Manager | Project Initiation plan
Hard copy delivery
Kickoff Meeting | Project Sponsor | Introduce the project team and the project. Review project objectives and management approach. Communicate plans and stakeholder roles/responsibilities | Meeting (Face to Face) | Near Project Start Date | Project Manager | Agenda
| Project Team |  |  |  |  | Meeting Minutes
Stakeholders
Project Information | Project Sponsor | Deliver important messages across to necessary recipients | Meeting | As needed | Project Manager | Project updates
| Stakeholders |  | Emails
| Project Team |  | Conference calls
Project Status Report |  | Update stakeholders on the detailed progress of the project | Face to Face/ Virtual Presentation | Monthly | Project Manager | Project status report
| All stakeholders |  | Written Report
Emails
Template: Status report
Biweekly reports | Management | Update management on the status of the project (achievements and outstanding) | Reports | Every Two Weeks | Project Manager | Project weekly report
Meetings
Project Risk | Project Team | Communicate risk faced by the project, unforeseen risk and mitigation resolution if any | Risk Document | As Needed | Project Manager | Project Risk
|  |  | Meetings |  |  | Project Mitigation plan
Agenda/Minutes | Project Team | Distribution of minutes taken during meetings together with action points | Emails | After Every Meeting | Project Manager | Minutes
SharePoint
Team Meetings | Project team | Group meetings/ | Meetings (Face to face/ Virtual) | Weekly | Project Manager | Status Reports
Individual meetings for sub-teams, and functional team to review detailed plans (Task, assignments and action items)